# <LSDS Project>

# Project Risk Management Plan

<Sibin Jacob>

<CIS 633 Managing Project Risks>

<06/02/2025>

<sibinjacob115@gmail.com>

# VERSION HISTORY

| Version # | Implemented By | Revision Date | Approved By | Approval Date | Reason |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Sibin Jacob | 4/6/25 | <Sibin Jacob> | 4/6/25 | Sections 1, 2, 3, and 9 |
| 2.0 | Sibin Jacob | 4/20/25 | Sibin Jacob | 4/22/25 | Complete sections 6, 7, 8 |
| 3.0 | Sibin Jacob | 4/27/25 | Sibin Jacob | 4/27/25 | Updated columns 6,7, & 8 of the risk register. Completed Sections 4 & 5. |
| 4.0 | Sibin Jacob | 5/10/25 | Sibin Jacob | 5/10/25 | Completed columns 9 & 10 of the Risk Register. Updated Appendix B and adding explanations on risk attitude columns under “Stakeholder Risk Tolerance” table. |
| 5.0 | Sibin Jacob | 5/18/25 | Sibin Jacob | 5/18/25 | Added information to “Tracking” and “Reporting Formats” sections. |
| 6.0 | Sibin Jacob | 6/2/25 | Sibin Jacob | 6/2/25 | Signed for approval. Completed Quality Methodologies section. |
| 7.0 | Sibin Jacob | 6/2/25 | Sibin Jacob | 6/2/25 | Final signatures. Updated risk status, budget, and time contingency tables. |

TABLE OF CONTENTS

1	introduction	5

2	Project Risk Management Processes & Methodology	6

3	Roles and Responsibilities	7

4	Budgeting	8

5	Timing	9

6	Risk Categories	10

7	Definitions of risk probability and Impact	12

8	probability and impact Matrix	12

9	Stakeholders Risk tolerences	13

10	Risk Register	15

11	Reporting Formats	17

12	Tracking	18

13	Quality Improvement Methodologies	19

Project Risk Management Plan Approvals	20

APPENDIX A: REFERENCES	21

APPENDIX B: KEY TERMS	22

# introduction

LSDS contracted with ASDG to develop and deliver a project risk management training to train team members and produce the following outputs and activities:

- Develop a LSDS project management plan

- Document a risk register, tracks and prioritizes risks or uncertainties, either resulting in positive or negative results.

- Perform Qualitative and Quantitative Risk Analysis

- Risk management to improve quality

- Monitor, control, and manage risk events when they become issues

The overall objective of this Project Risk Management Plan is to help ensure a common understanding among project stakeholders of how uncertainties for the project are planned to be identified, evaluated, categorized, prioritized, documented, and managed for the LSDS project.

This Project Risk Management Plan defines the roles and responsibilities to be undertaken, explains the processes to be used, identifies uncertainties, and provides a plan for managing uncertainties associated with the client’s project.  It essentially outlines an understanding to be achieved among stakeholders regarding the processes and actions necessary to facilitate ensuring uncertainties do not preclude project success.

The intended audience of the LSDS Project Risk Management Plan is the client project sponsor, contractor program manager, project manager, project team, senior leaders, and any other stakeholder whose support is needed to carry out the planning and managing of uncertainties for the client’s project.

# Project Risk Management Processes & Methodology

| Risk Management Process/Activity | Risk Management Process / Activity Description | Ownership |
| --- | --- | --- |
| Risk Identification | Risks identified at the start of each phase and during milestone reviews. | Sibin Jacob |
| Qualitative Risk Analysis | Risks prioritized using the probability and impact matrix (Vicente, 2024). Each identified risk will be rated for severity and likelihood to determine its exposure. For clarity, risks wills be categorized as technical, financial, external, etc. | Elizabeth |
| Quantitative Risk Analysis | A method of risk assessment that uses numerical data and statistical techniques to quantify likelihood and impact of potential risks (Project Management Academy, 2025). Monte Carlo and severity analysis will be performed for high-priority risks. Schedule and costs are accounted for with these tools. | Chamroeun |
| Risk Response Technique | Strategies developed for both threats and opportunities. These choices include avoidance, mitigation, transfer, and acceptance for threats, enhancement, exploitation, and sharing opportunities (Nizhebetskyi, 2023). | Sibin Jacob |
| Risk Monitoring and Control | Continuous risk tracking through regular status meetings, phase reviews, and risk register updates (PMI, 2025). New risks are added. Indicators and triggers are monitored. | Raji |

# Roles and Responsibilities

| Risk Management Activity Role | Risk Management Responsibility | Assignment | Risk Attitude |
| --- | --- | --- | --- |
| Risk Manager | Oversees the entire risk process. | Elizabeth | Low |
| PMO (Project Management Officer) | Supports consistent risk management practices to align with organization risk policies and assists in documentation (Project Management Academy, 2025). | Alu | Low |
| Cost Controller | Defines and tracks the project’s costs. Provides input for quantitative risk analysis. | Chamroeun | Low |
| Scheduler | Scheduling project timeline and identifying risks | Raji | Low |
| Stakeholder Engagement Lead | Stakeholder communication about risks. Supports risk manager in compliance and regularly contributes to risk reporting, | Tom | Low |
| The Project Manager | Responsible for planning, executing, and overseeing projects to ensure they are completed on time. | Sibin | Low |
| Risk Analyst | Professional who evaluates and manages potential risks that can impact an organization’s finances, operations, or reputation (Project Management Academy, 2025) | Lucy | Low |

# Budgeting

Using the qualitative probability and magnitude from the Risk Register, the Expected Monetary Value for each threat-type risk and total is estimated for our contingency reserve, which covers known-unknowns tied to the risks identified analyzed in the risk register. The amount is tracked and requested through a formal change request process, which requires approval by the sponsor and project manager (PMI, 2025).

EMV (Expected Monetary Value) = Probability x Impact

Table below explaining EMV-based estimate:

| Risk Description | Probability | Impact ($) | EMV |
| --- | --- | --- | --- |
| Integration compatibility with Jupiter Systems | Medium (0.5) | $8000 | $4000 |
| Staff Turnover of LSDS or ASDG | Medium (0.4) | $6000 | $2400 |
| Inadequate access to LSDS data | High (0.8) | $7000 | $5600 |
| Jupiter’s misalignment with LSDS | Medium (0.5) | $5000 | $2500 |
| Failure to deliver training | Low (0.2) | $10000 | $2000 |
| Negative Feedback from LSDS | Medium (0.4) | $6000 | $2400 |
| LSDS Project Managers not accepting ASDG training | Medium (0.4) | $5000 | $2000 |
| Total Contingency Reserves |  |  | $20,900 |

Reserve Usage Protocol:

Contingency Reserve: When a documented risk from the risk register requires approval by the project manager with documentation and justification.

Management Reserves: Only if unforeseen risks or strategic decisions are outside of the scope of identified risks.

# Timing

| Risk Description | Probability | Time Impact (Days) | Contingency Time (Days) |
| --- | --- | --- | --- |
| LSDS’s Project Managers not accepting ASDG training | Medium (0.4) | 5 days | 2 days |
| Staff Turnover | Medium (0.4) | 4 days | 1.6 days |
| Access Delays To LSDS Data | High (0.8) | 7 days | 5.6 days |
| Misalignment with Jupiter’s values | Medium (0.4) | 3 days | 1.2 days |
| Failure to Deliver Training | Low (0.2) | 7 days | 1.4 days |
| Negative Feedback from LSDS | Medium (0.4) | 4 days | 1.6 days |
| Compatibility with Integration | Medium (0.5) | 6 days | 3.0 days |
| Total Schedule Contingency |  |  | 16.4 days |

Contingency Time (Days) = Probability x Time Impact (Days)

Reserve Usage Protocol

Schedule Contingency: Proactively applied after a known risk occurs. The Project Manager (PM) needs to adjust the schedule and present a justification to the project sponsor.

Schedule Management Reserve: Requires selection from the sponsor and Project Manager (Project Management Academy, 2025). SMR only approves critical impacts to scope, client-driven changes, or emerging risks.

# Risk Categories

Technical Risks: Encompasses technological failures, cyberattacks, data breaches, or the obsolescence of technology (MetricStream, 2025).

- Issues with integration between Jupiter Systems and LSDS.

- Compatibility issues with current infrastructure

- Implementation of new tools

Financial Risks: Risks related to financial market, investment, and current exchange rates (MetricStream, 2025).

- Unexpected costs with training

- Overbudget

- Budget adjustments due to tools or delays

Strategic Risks: Relates to the organization’s overall goals and objectives, such as from failed business decisions, market changes, or changes in the competitive landscape (MetricStream, 2025).

- Training program fails to meet LSDS’s expectations

- ASDG’s performance affects their reputation and future opportunities

Organizational Risks: Internal structure and functions of the organization, which includes lack of stakeholder engagement alignment, internal resistance to change, and miscommunication between departments (MetricStream, 2025).

- Poor coordination between ASDG and LSDS departments

- LSDS project managers

Reputational Risks: affect public’s perception of either company and impact relationships with partners, clients, and stakeholders.

- Negative feedback from public or LSDS team about ASDG’s performance

- Failure to deliver an adequate or robust training program.

Compliance Risks: Failure to adhere to regulatory requirements and industry standards (MetricStream, 2025).

- Mishandling of classified information from LSDS

- Documentation of risk procedures are incomplete or fail to meet LSDS’s audit requirements.

Operational Risks: Potential for financial loss or disruption in business operations due to external events, human errors, or internal failures (MetricStream, 2025)

- Staff turnover for either ASDG or LSDS teams

- Lack of access to system or workplace needed for training

- Security breaches

- Scheduling issues

Opportunities:

- Increase collab with future contracts

- Development of reusable risk training

# Definitions of risk probability and Impact

(PMBOK, p. 318)

# probability and impact Matrix

(PMBOK, p. 331)

# Stakeholders Risk tolerences

| STAKEHOLDER REGISTER |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name/Group | Project Role | Risk Attitude | Major Requirements | Major Expectations | Potential Influence |
| Maxwell Maximillian LSDS CIO | Customer Project Sponsor | Low – Expectations are on results and strategy. Prefers minimized risks. Aligns with reliable delivery and reputation. | Personnel project risk management training and support. | Expects training will add value to personnel by equipping them to manage uncertainties in this and other projects. | If pleased with ASDG work, could influence obtaining future contracts. Could influence ASDG reputation among other corporations. |
| Bill Baumbas LSDS most senior project manager | LSDS primary contact | High – accepts and manages risks. Shows an openness to change and is willing to engage is deeper level training. | Training materials, documented procedures, and templates | Expects he and his colleagues will learn considerably more about project risk management. | Could have direct influence on Maxwell’s perception of ASDG performance. Could have direct influence on colleague’s perspectives. |
| Harry, Karrie, Fred, Fran, Larry, Lucy, Bart, and Barry LSDS project managers | LSDS project managers who will training and working with directly | High – has a growth mindset, the willingness the learn and apply risk management practices. They will implement changes. | Training materials, documented procedures, and templates, hands-on use and guidance of use of these | Expect they will learn considerably more about project risk management and have an opportunity to practice what is trained. | Arguably the most influential since it will be their evaluations of ASDG performance that get forwarded first to Bill and then Maxwell. |
| Tom Terrifick ASDG Program Manager (a Senior VP) | Your boss | Medium – balance of caution and calculations. | Excellent performance reports from LSDS CIO. | Expects ASDG excellent performance to garner future LSDS contracts and further ASDB reputation in the industry | Could influence your next promotion and future advancement. One of you key sources of advice and guidance |
| Your team | Tom and Raji will be working on site with you. Elizabeth, Alu, and Chamroeun will be backup resources in the office to support research and materials development | Low - My team is directly focused on support and execution of the project. We require transparent instructions, easy access to data, and a structured work environment. | Tom and Raji need onsite work area where they can to their work individually and with the client. Access to a classroom they can schedule. Access to LSDS sensitive information. Elizabeth, Alu, and Chamroeun need clear direction from the field to produce their deliverables | Expect to be treated professionally and given latitude to make independent decisions for up to the moderately critical issues. Expect clear channels of communication with LSDS as well as ASDG. Elizabeth, Alu, and Chamroeun also expect clear communication channels to obtain clarification of deliverable requirements | Directly influence ASDG performance on this contract. Directly influence relationships with all LSDS personnel. They are the ASDG face LSDS sees. |
| Jim Jagger Jupiter Systems COO | LSDS liaison with Jupiter Systems; owns the operating system developers | High – in coordination and innovation. | Requires close coordination with LSDS Key Stakeholders | Expects LSDS to effectively manage the project | Can influence the LSDS performance evaluations of ASDG; Could influence ASDG reputation among other corporations. |
| Ada Cody | Director of Jupiter Systems Software Development; manages the operating system developers | Low - development execution and ensuring that Jupiter Systems is aligned with LSDS. | Requires close coordination with LSDS Key Stakeholders | Expects LSDS to effectively manage the project | Can influence the LSDS performance evaluations of ASDG |
| William Whizzer | Senior Software Developer; Jupiter Systems Software Technical Lead and onsite Jupiter Representative | Low – prioritizes clarity and predictability over taking risks. Has a cautious approach | Requires close coordination with LSDS Key Stakeholders and daily participation with the project team | Expects LSDS to effectively manage the project; expects to be heard | Serves as conduit of information to Jim and Ada, thus can influence those who influence the LSDS performance evaluations of ASDG |

# Risk Register

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Date Risk Identified | Description of Risk | Risk Category | Constraint Impacted | T ¦ O | Probability of Occurring | Magnitude of Effect | EMV | Response Strategy and Plan | Owner | Status |
| 4/20 | LSDS project managers not accepting new approaches introduced by ASDG risk training. | Organizational | Quality, schedule | T | Medium | High | High | Mitigate - Conduct early engagement meetings, provide adaptation support materials. | ASDG Risk Training Lead | In Progress |
| 4/20 | Compatibility with integration of Jupiter Systems and LSDS. | Technical | Cost, time | T | High | High | High | Mitigate - Schedule technical workshops. | ASDG Technical Lead | Monitoring |
| 4/20 | High engagement with project managers resulting in templates reused for future contracts. | Strategic | Quality, cost | O | Medium | Medium | Medium | Enhance - Use standardized templates and gather feedback for improvements. | ASDG PMO | Open |
| 4/20 | Potential staff turnover for either or both ASDG and LSDS teams | Operational | Time, quality | T | Medium | High | Medium | Mitigate - Cross-train key staff members | HR Leads | Monitoring |
| 4/20 | Inadequate access to LSDS’s sensitive information/data, causing delay for training content development. | Operational | time | T | High | Medium | High | Mitigate - Define secure access protocols early. | Data Managers | In Progress |
| 4/20 | Stakeholder’s both positive and improvement feedback leads to a strong performance evaluation for ASDG teams. | Strategic | Reputation | O | Medium | High | High | Enhance- Showcase lessons learned from past projects and in future proposals. Create feedback loops. | ASDG Team Lead | Open |
| 4/20 | Staff of Jupiter Systems misalignment with LSDS’s expectations, delivery miscommunication. | Organizational | Quality | T | Medium | Medium | Medium | Mitigate - Clarify roles and expectations through meetings. | Project Manager | In Progress |
| 4/20 | Newly developed risk training modules for other internal projects by LSDS | Strategic | Time, cost | O | Medium | Medium | Medium | Exploit - Provide documentation and training framework for reusage. | LSDS Training Coordinator | Open |
| 4/20 | Failure to deliver an adequate training program | Reputational | Quality, reputation | T | Low | High | High | Mitigate - Gather feedback and adjust curriculum as needed. | ASDG Training Lead | Monitoring |
| 4/20 | LSDS’s negative feedback about ASDG’s performance | Reputational | Quality, reputation | T | Medium | High | High | Mitigate - Set clear evaluation metrics early and continue to maintain ongoing communication with LSDS team. | ASDG Manager | In Progress |
| 5/10/25 | Cross collaboration between LSDS, ASDG, and Jupiter Systems leads to best practices and innovation adopted into future and current projects. | Strategic | Quality, time | O | Medium | High | High | Enhance - Document and share success stories, encourage regular knowledge joint perspective sharing sessions. | ASDG Project Manager | In Progress |

# Reporting Formats

The primary format used to communicate risks for this project is the Risk Register, which includes the following details for each entry:

- Date identified

- Description

- Category

- Constraints

- Type (Opportunity or Threat)

- Probability

- Magnitude of Effect

- Expected Monetary Value (EMV)

- Response Strategy & Plan

- Owner

- Risk Status

The risk register is in a structured table format and is regularly updated. High-risk items are visibly highlighted. Updates are tracked by the “Status” column. The outcomes of risk management processes are emerging risks, mitigation actions taken, probability and impact, and lessons learned.

They are, documented in the risk register and project documentation, analyzed during project review meetings with key stakeholders to address trends and evaluate effectiveness, communicated through biweekly status updated and shared with LSDS contacts and ASDG leaders, and are part of the final documentation. Lessons learned are summarized in the Project Closure Report, with emphasis that includes successful mitigation strategies, challenges faced, and recommendations for future projects (PMI, 2021).

# Tracking

All risk-related activities are documented and tracked through the risk register, which is the central repository for all identified risks, analysis, response strategies, and updates throughout the project timeline (PMI, 2021).

The Risk Register will be updated on a regular basis by the assigned risk responsibilities and reviewed during project meetings. Updates will include response actions taken, status changes, or any newer risks. For traceability and transparency, each risk will have information such as probability, impact, mitigation progress, or ownership changes.

Risk management processes will be evaluated by:

- Risks were identified and assessment in a timely manner

- Response plans and mitigation executed as intended

- New risks documented appropriately

- Risk outcomes affected by stakeholders

Missed or mishandled managed risks will be flagged during reflections or post-project reviews, as this will examine if the correct management tools and techniques were implemented and to identify gaps in the plan ().

Findings from the audit will be used to guide future risk management practices in LSDS and ASDG. They will be recorded in the project’s Lessons Learned document for reference.

# Quality Improvement Methodologies

Quality improvement methodologies are essential for identifying and managing project risks, ensuring deliverables meet stakeholder expectations and prevent defects (AtlexSoft, 2023). With risk management integration, there are two types of Quality Improvement Methodologies to be used: Quality Assurance and Quality Control.

Quality Assurance (QA) focuses on process-oriented, proactive measures to prevent failures or defects in project deliverables (AtlexSoft, 2023). QA implements risk-aware processes, which ensures they are built with risk controls, safeguards, and checkpoints. It serves as an early identification of process-based risks through planning, process audits, and standard adherence checks. QA helps surface risks related to poor documentation, communication gaps, or workflow inefficiencies. In addition, Quality Assurance encourages key principles such as feedback loop and retrospectives, which supports lessons learned. For example, during training development for LSDS. the QA methods such checklists. peer reviews, and review gates ensure the quality and alignment of deliverables.

QA implements risk-aware processes, which ensures they are built with risk controls, safeguards, and checkpoints. It serves as an early identification of process-based risks through planning, process audits, and standard adherence checks. QA helps surface risks related to poor documentation, communication gaps, or workflow inefficiencies. In addition, Quality Assurance encourages key principles such as feedback loop and retrospectives, which supports lessons learned. For example, during training development for LSDS. the QA methods such checklists. peer reviews, and review gates ensure the quality and alignment of deliverables.

Quality Control (QC) is reactive and product-oriented, as it focuses on detecting and correcting defect. QC verifies deliverables against requirements by identifying errors before the deliverables reach stakeholders, reducing delivery and reputational risks. Through frequent inspections and testing cycles, QC detect emerging risks, which can be documented in the risk register. When defects are detected, QC triggers corrective actions such as reallocation of resources, rework, and/or timeline adjustments. If a training module fails to meet LSDS standards during a run through, QC will prompt the team to identify the root causes and take immediate action to manage the risk before deployment.

Both Quality Assurance and Quality Control create a reiterative loop that reduces uncertainty, enhance stakeholder confidence, and supports the risk management objectives of maximizing opportunities and minimizing threats. Integrating both methodologies allow ASDG and LSDS to continuously arrange quality-related risks to aim for a successful delivery of the project’s training and outcomes.

Project Risk Management Plan Approvals

The undersigned acknowledge they have reviewed the <LSDS> Project Risk Management Plan and agree with the approach it presents.  Changes to this Project Risk Management Plan will be coordinated with and approved by the undersigned or their designated representatives.

| Signature: | Sibin Jacob | Date: | 6/2/25 |
| --- | --- | --- | --- |
| Print Name: | Sibin Jacob |  |  |
| Title: | Project Manager |  |  |
| Role: | Lead Project Manager ASDG |  |  |

| Signature: | Tom Terrifick | Date: | 6/2/25 |
| --- | --- | --- | --- |
| Print Name: | Tom Terrifick |  |  |
| Title: | ASDG Program Manager (a Senior VP) |  |  |
| Role: | Head of ASDG |  |  |

| Signature: | Maxwell Maximillian | Date: | 6/2/25 |
| --- | --- | --- | --- |
| Print Name: | Maxwell Maximillian |  |  |
| Title: | LSDS CIO |  |  |
| Role: | Project Sponsor, LSDS |  |  |

APPENDIX A: REFERENCES

| Document Name and Version | Description | Location |
| --- | --- | --- |
| PMBOK, 5th ed. | Guide to the Project Management Body of Knowledge | Project manager’s personal desk copy. |
| Cflow (2025, March 24) | Project Risk Management: A Comprehensive Guide For Project Managers | https://www.cflowapps.com/project-risk-management-guide/ |
| MetricStream. (2025). | What are risk categories? Types and ways to determine them. | https://www.metricstream.com/learn/what-are-risk-categories.html​Metricstream |
| Nizhebetskyi, D. (2023, September 17). | Risk response strategies (Definitive guide with examples). IT PM School. | https://itpmschool.com/risk-response-strategy/ |
| Stanford University IT. (2025). | Risk Classifications | https://uit.stanford.edu/guide/riskclassifications |
| Project Management Academy. (2025). | Risk Management Process For PMT | https://projectmanagementacademy.net/resources/risk-management-process-for-pmp/ |
| Vicente, V. (2024, February 15). | Risk Assessment Matrix: Overview and Guide | https://www.auditboard.com/blog/what-is-a-risk-assessment-matrix/ |
| Aldridge, E. (2022). Project Management Academy | Using Contingency and Schedule Reserve in Your Projects. | https://projectmanagementacademy.net/resources/blog/using-contingency-and-schedule-reserve-in-your-projects/ |
| AltexSoft. (2023). | Quality Assurance (QA), Quality Control and Testing. | https://www.altexsoft.com/whitepapers/quality-assurance-quality-control-and-testing-the-basics-of-software-quality-management/ |

APPENDIX B: KEY TERMS

| Term | Definition |
| --- | --- |
| Risk | Used synonymously with the term uncertainty |
| Uncertainty | Used synonymously with the term risk |
| Risk Attitude | A person’s or organization’s chosen response to uncertainty that can impact project objectives (PMI, 2025) |
| EMV (Expected Monetary Value) | Calculated by probability * impact. The calculation helps determine the average financial gain or loss expected from a decision to consider different outcomes. |
| Probability | Likelihood of a specific outcome occurring |
| Impact | The extend of an event affecting a risk organization |